4-Week Project Plan: Scalable Smart Home Lighting System

This plan outlines the daily tasks for completing the project within a four-week timeline. It assumes a 7-day work week for planning purposes, but the weekend days are lighter and focused on review and preparation.

Week 1: Foundation, Architecture, and Basic Data Flow

Goal: Establish the project foundation, design the architecture, and create a simple, end-to-end data flow from a simulated sensor to the AWS cloud.

- Day 1: Project Kickoff & Planning

  - Thoroughly review the project proposal and requirements document.

  - Set up a Git repository (e.g., on GitHub) for version control.

  - Create an initial README.md file with a project overview.

  - Initialize a local Node.js project.

- Day 2: AWS Environment Setup

  - Configure your AWS account.

  - Create an IAM (Identity and Access Management) user with administrative permissions for your work to follow security best practices.

  - Set up the AWS CLI on your local machine with your new IAM user credentials.

  - Research the AWS services you'll be using: IoT Core, Lambda, DynamoDB, and API Gateway.

- Day 3: System Architecture & Data Design

  - Refine the high-level block diagram of the system.

  - Design the data schema for DynamoDB. Finalize the attributes for SensorData, LightStates, and UserRules tables.

  - Define the MQTT topic structure (e.g., iot/sensors/livingroom/light or iot/commands/livingroom/light1).

- Day 4: AWS IoT Core & Device Simulation

  - In AWS IoT Core, create a "Thing" to represent your first simulated sensor.

  - Generate and securely save the device certificates and policies.

  - Write a simple Python or Node.js script to act as your simulated ambient light sensor. This script will use the MQTT protocol and the device certificates to connect to AWS IoT Core.

- Day 5: First Data Ingestion

  - Have your script publish simulated data (e.g., { "light_intensity": 450 }) to an MQTT topic.

  - Use the MQTT test client in the AWS IoT Core console to subscribe to the topic and verify that messages are being received.

  - Troubleshoot any connection or data format issues.

- Day 6: Database Setup & Basic Logging

  - Create the SensorData DynamoDB table in AWS with the schema designed on Day 3.

  - Create a simple AWS IoT Rule that triggers on a message publication and sends the message data to a CloudWatch Log group for basic logging.

- Day 7: Weekly Review & Lookahead

  - Review the week's progress against the plan.

  - Consolidate all notes and diagrams.

  - Read documentation for AWS Lambda and API Gateway to prepare for Week 2.

Week 2: Core Logic, Automation, and Full Simulation Loop

Goal: Process the incoming data, implement automation logic using Node-RED, and create a complete, simulated loop from sensor input to actuator output.

- Day 8: Data Processing with Lambda

  - Create a Node.js-based AWS Lambda function named SensorDataProcessor.

  - Modify the AWS IoT Rule from Day 6 to trigger this Lambda function instead of logging to CloudWatch.

  - Write code in the Lambda function to parse the incoming sensor data and write it to the SensorData DynamoDB table.

- Day 9: Actuator Simulation

  - Create a second Lambda function called SimulatedLightActuator. This function's job is to log a message like "Light [lightId] turned [ON/OFF]".

  - Set up an AWS API Gateway endpoint that triggers this Lambda function. This will be your "dummy API" for controlling the light.

  - Test the API endpoint using a tool like Postman or curl to ensure it triggers the Lambda correctly.

- Day 10: Node-RED Setup

  - Set up a local instance of Node-RED.

  - Install the necessary nodes for AWS connectivity (node-red-contrib-aws-iot-device or similar) and dashboard creation (node-red-dashboard).

  - Configure Node-RED to connect to your AWS IoT Core instance to subscribe to sensor data topics.

- Day 11: Basic Automation Flow

  - Create a simple Node-RED flow:

    - An mqtt in node to receive sensor data from AWS IoT.

    - A switch node to implement a rule (e.g., "if light_intensity < 300").

    - An http request node that calls your simulated actuator API Gateway endpoint to "turn the light on".

- Day 12: Enhancing the Automation Flow

  - Add a second output to the switch node to handle the "turn light off" condition (e.g., if light_intensity >= 300).

  - Implement a simple UI using node-red-dashboard to show the current sensor value and the simulated light state.

- Day 13: Error Handling & State Management

  - Improve your Node-RED flow and Lambda functions with basic error handling.

  - Create the LightStates DynamoDB table.

  - Modify your SimulatedLightActuator Lambda to write the new state ("ON" or "OFF") to the LightStates table.

- Day 14: Weekly Review & Full Loop Test

  - Test the entire simulated loop: Sensor script -> AWS IoT -> Lambda -> DynamoDB -> Node-RED -> API Gateway -> Actuator Lambda -> DynamoDB.

  - Document the completed flow with screenshots.

  - Prepare for scalability testing by brainstorming how to simulate many devices.

Week 3: Scalability Testing, Security, and Deployment

Goal: Deploy the solution to a more robust environment, conduct and document scalability experiments, and implement security and monitoring best practices.

- Day 15: Security Hardening

  - Review IAM roles and policies. Ensure they follow the principle of least privilege (i.e., only grant the permissions necessary).

  - Review the IoT device policy to ensure it can only publish/subscribe to its designated topics.

  - Add authentication/authorization to your API Gateway endpoint (e.g., using an API key).

- Day 16: Monitoring & CloudWatch Dashboards

  - In AWS CloudWatch, create a custom dashboard.

  - Add widgets to monitor key metrics: Number of IoT messages, Lambda invocations, Lambda error rates, and DynamoDB read/write capacity units.

- Day 17: Planning the Scalability Test

  - Define the test parameters: How many virtual devices? For how long? What message frequency?

  - Write a plan for what metrics to capture and how to analyze them to prove scalability.

- Day 18: Developing the Load-Test Script

  - Create a new, advanced Node.js or Python script that can simulate hundreds or thousands of concurrent devices.

  - This script should read device certificates, connect to AWS IoT, and publish messages on unique topics for each simulated device.

- Day 19: Executing Scalability Test v1

  - Run the load-test script with a moderate load (e.g., 100 devices).

  - While the test is running, actively monitor your CloudWatch dashboard.

  - Capture screenshots of the dashboard graphs. Note any errors, throttled requests, or performance degradation.

- Day 20: Analyzing Results & Optimization

  - Analyze the results from yesterday's test. Did any part of the system fail or slow down?

  - Based on the data, optimize the system. This might involve increasing Lambda memory, or changing the DynamoDB capacity mode from Provisioned to On-Demand to handle the spiky workload.

- Day 21: Weekly Review & Re-test

  - Run a second, larger scalability test (e.g., 500-1000 devices) on the optimized system.

  - Document the improved results, demonstrating how your changes enhanced scalability.

  - Organize all your test evidence (screenshots, logs, metrics).

Week 4: Finalization, Documentation, and Submission

Goal: Finalize the project code, write the comprehensive final report, and prepare all materials for submission.

- Day 22: Code Refinement and Cleanup

  - Review all your code (sensor scripts, Lambda functions, test scripts).

  - Add comments where necessary to explain complex logic.

  - Ensure your code is clean, well-organized, and follows best practices.

- Day 23: Finalizing the GitHub Repository

  - Update the README.md to be a complete guide. It should include:

    - A project description.

    - The final architecture diagram.

    - Instructions on how to set up and deploy the system.

    - Instructions on how to run the simulation and scalability tests.

  - Ensure all code, including Node-RED flows (export as JSON), is committed and pushed to the repository.

- Day 24: Writing the Project Report (Sections 1-2)

  - Start writing the final report document.

  - Section 1: High-Level Problem Analysis. Describe the problem, stakeholders, and requirements.

  - Section 2: Solution Design. Detail your architecture with the block diagram, data models, and technology choices.

- Day 25: Writing the Project Report (Sections 3-4)

  - Section 3: Deployment and Scalability Evidence. This is crucial. Embed the graphs and metrics from your scalability tests. Explain how the results demonstrate a scalable system.

  - Section 4: Discussion. Discuss the appropriateness of your solution, its limitations, and potential future improvements.

- Day 26: Compiling Evidence & Peer Review

  - Gather all required files: the final report (as a PDF), the link to your GitHub repository, and any other specified evidence.

  - If possible, have a peer or your tutor quickly review your report and GitHub repo for clarity and completeness.

- Day 27: Final Review & Submission Prep

  - Do a final check of all submission requirements from the project brief.

  - Create a checklist and tick off every single item.

  - Package all files into a single zip archive if required.

- Day 28: Submit!

  - Submit your completed project.

  - Congratulations on finishing your project

48.1s